## Projektplan
Projektplan | Gant-Schema
Aktivitet | Vecka
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Strategies & Social Contract
KPI
Product Backlog
Business Model
SPRINT 1
SPRINT 2
SPRINT 3
Half-Time Evaluation
SPRINT 4
SPRINT 5
Final Presentation: Working Prototype (APK) + Stakeholder Value
Final Presentation
Writing Reflections
Source Code + Output from GitInspector + Prototype + Reflection Report
[5 empty] | Planering |  |  | Dokumentera
[5 empty] | Design |  |  | Problemformulering
[5 empty] | Utveckla programvaran |  |  | Mål
[5 empty] | Ahlpa-test |  |  | Konceptuell modell
[5 empty] | Implementation |  |  | Indatamodullering
[5 empty] | Beta-test |  |  | Översätta k.modell till datamodell
[5 empty] | Utvärdering |  |  | Verifeira
Validera
Experimentera designen
Analysera experimenten
Fler körningar
Implementation
Utvärdera
Feedback

## Datum
Datum
Week | Läsvecka | Start Date | End Date | Topic | Deliverable | Time | Upload to | Email | Place |  |  | Supervision
v. 12 | 1 |  | 2017-03-24 | Strategies & Social Contract | D1 | 17.00 | Team Git Repo | Håkan B | -
v. 13 | 2 |  | 2017-03-31 | KPI | D2 | 17.00 | Team Git Repo | - | - | Week | LV | Date | Place | Done
v. 14 | 3 |  | 2017-04-04 | Product Backlog | D3 a | 17.00 | - | JS | -
v. 14 | 3 |  | 2017-04-07 | Business Model | D3 b | 17.00 | Team Git Repo | - | - | v. 16 | 4 | 2017-04-19 | Lindholmen | X
v. 16 | 4 | 2017-04-19 | 2017-04-26 | SPRINT 1 | P + R | 12.00 | Google Drive |  | -
v. 17 | 5 | 2017-04-26 | 2017-05-03 | SPRINT 2 | P + R | 12.00 | Google Drive |  | -
v. 18 | 6 | 2017-05-03 | 2017-05-10 | SPRINT 3 | P + R | 12.00 | Google Drive |  | -
v. 19 | 7 |  | 2017-05-10 | Half-Time Evaluation | D4 | 15.00 | Team Git Repo | - | - | v. 17 | 5 | 2017-04-26 | Lindholmen
v. 19 | 7 | 2017-05-10 | 2017-05-17 | SPRINT 4 | P + R |  | Google Drive
v. 20 | 8 | 2017-05-17 | 2017-05-24 | SPRINT 5 | P + R |  | Google Drive
v. 21 | 9 |  | 2017-05-22 | Final Presentation: Working Prototype (APK) + Stakeholder Value | D5 | 13.00 | Team Git Repo | - | - | v. 18 | 6 | 2017-05-03 | Lindholmen
v. 21 | 9 |  | 2017-05-24 | Final Presentation |  | 10.00 - 12.00 | - | - | Visual Arena | v. 19 | 7 | 2017-05-10 | Lindholmen
v. 22 | 10 |  | ? | Writing Reflections |  | 13.15 - 15.00 | - | Håkan B | Lindholmen | v. 20 | 8 | 2017-05-17 | Lindholmen
v. 22 | 10 |  | 2017-06-02 | Source Code + Output from GitInspector + Prototype + Reflection Report | D6 | 17.00 | Team Git Repo | - | -
Sprints
Week | Läsvecka | Start Date | End Date | Sprint beskrivning | Sprint number |  | Planning | Reflection
v. 16 | 4 | 2017-04-19 | 2017-04-26 | Första sprint | Sprint 1 |  | 2017-04-19 | 2017-04-26
v. 17 | 5 | 2017-04-26 | 2017-05-03 | Kriga sprint | Sprint 2 |  | 2017-04-26 | 2017-05-03
v. 18 | 6 | 2017-05-03 | 2017-05-10 | Kriga sprint | Sprint 3 |  | 2017-05-03 | 2017-05-10
v. 19 | 7 | 2017-05-10 | 2017-05-17 | Kriga sprint | Sprint 4 |  | 2017-05-10 | 2017-05-17
v. 20 | 8 | 2017-05-17 | 2017-05-24 | Presentations-sprint | Sprint 5 |  | 2017-05-17 | 2017-05-24

## Milstolpar
Milstolpar
Week | Läsvecka
v. 12 | 1
v. 13 | 2
v. 14 | 3
v. 15 | PÅSKLOV
v. 16 | 4 | Sprint 1
v. 17 | 5 | Sprint 2
v. 18 | 6 | Sprint 3
v. 19 | 7 | Sprint 4
v. 20 | 8 | Sprint 5
v. 21 | 9
v. 22 | 10

## Anteckningar
Anteckningar
Deliverables
Week | Läsvecka | Date | Topic | Deliverable | Time | Upload to | Email
| 1 | 2017-03-24 | Strategies & Social Contract | D1 | 17.00 | Team Git Repo | Håkan B
| 2 | 2017-03-31 | KPI | D2 | 17.00 | Team Git Repo | -
| 3 | 2017-04-04 | Product Backlog | D3 a | 17.00 |  | JS
| 3 | 2017-04-07 | Business Model | D3 b | 17.00 | Team Git Repo
| 7 | 2017-05-10 | Half-Time Evaluation | D4 | 15.00 | Team Git Repo
| 9 | 2017-05-22 | Final Presentation: Working Prototype (APK) + Stakeholder Value | D5 | 13.00 | Team Git Repo
| 11 | 2017-06-02 | Source Code + Output from GitInspector + Prototype + Reflection Report | D6 | 17.00 | Team Git Repo
Week | Läsvecka | Date | Topic | Deliverable | Time | Upload to | Email | Place
v. 12 | 1 | 2017-03-24 | Strategies & Social Contract | D1 | 17.00 | Team Git Repo | Håkan B | -
v. 13 | 2 | 2017-03-31 | KPI | D2 | 17.00 | Team Git Repo | - | -
v. 14 | 3 | 2017-04-04 | Product Backlog | D3 a | 17.00 | - | JS | -
v. 14 | 3 | 2017-04-07 | Business Model | D3 b | 17.00 | Team Git Repo | - | -
v. 19 | 7 | 2017-05-10 | Half-Time Evaluation | D4 | 15.00 | Team Git Repo | - | -
v. 21 | 9 | 2017-05-22 | Final Presentation: Working Prototype (APK) + Stakeholder Value | D5 | 13.00 | Team Git Repo | - | -
v. 21 | 9 | 2017-05-24 | Final Presentation |  | 10.00 - 12.00 | - | - | Visual Arena
v. 22 | 10 | ? | Writing Reflections |  | 13.15 - 15.00 | - | Håkan B | Lindholmen
v. 22 | 10 | 2017-06-02 | Source Code + Output from GitInspector + Prototype + Reflection Report | D6 | 17.00 | Team Git Repo | - | -